## Master Calendar
Department | Unit | Type of Review | Phase 1 Start Date | Phase 1 End Date/Phase 2 Start date | Phase 2 End Date/Phase 3 Start Date | Phase 3 End Date/Review Completed |  | Committee Chair | Department Director | Notes
Digital Marketing* | Communications & Marketing | Full | 5/20/21 Andy will discuss with Khalil and Randy to determine what department will go first.
Planned Giving | Development | Alternate | 2022-01-01 | 2022-07-01 | 2022-10-01 | 2022-11-02 |  | Sheila Smith | Kathy Sarver
Gifts and Records | Information Services | Full | 4/2020 on hold due to director retirement | [6 empty] | Director retirement - delayed
Branded Content* | Communications & Marketing | Full | 5/20/21 Andy will discuss with Khalil and Randy to determine what department will go first.
Corp/Found Rel.* | Development | Full | 11/2018 on hold due to staffing change - department split into two
Parent Relations | Constituent Engagement | Alternate | 12/2019 on hold
Reporting | Information Services | Alternate | 2021-03-26 | [6 empty] | Director left and department merged with ABA
Strategic Gifts | Development | Alternate | 2023-07-01 | 2023-01-01 | 2023-04-01 | 2023-05-02 |  |  |  | Director left and department merged with ABA
Annual Giving | Constituent Engagement | Full | 2024-02-15 | 2024-08-15 | 2024-11-15 | 2024-12-15
Communications | Communications & Marketing | Full | 2024-06-11 | 2024-12-11 | 2025-03-31 | 2026-04-30
COMPLETED REVIEWS
Department | Unit | Type of Review | Phase 1 Start Date | Phase 1 End Date/Phase 2 Start date | Phase 2 End Date/Phase 3 Start Date | Phase 3 End Date/Review Completed | Time to Complete | Committee Chair | Department Director
Annual Giving | Development | Alternate | 2011-01-01 | 2011-03-31 | 2011-08-15 | 2011-09-15 | 9 months | Andy Perrine | Sheila Smith
Donor Relations | Constituent Relations | Full | 2011-04-01 | 2011-09-30 | 2012-01-15 | 2012-02-15 | 10 months | Chris Pipkins | Linda Elliott
Alumni Relations | Constituent Relations | Alternate | 2011-07-01 | 2011-09-30 | 2011-12-31 | 2012-01-31 | 6 months | Weston Hatfield | Ashley Privott
Prospect Research | Information Services | Full | 2012-01-01 | 2013-09-30 | 2013-12-20 | 2014-01-31 | 2 years | Steve Smith | Martin O'Donoghue
Planned Giving | Development | Full | 2012-04-01 | 2013-04-30 | 2013-05-31 | 2014-07-08 | 2 years | Chris Pipkins | Susan Fersner
Gifts and Records | Information Services | Full | 2013-06-01 | 2013-11-30 | 2014-04-30 | 2014-06-05 | 1 year | Sheila Smith | Brenda Nester
Marketing | Communications & Marketing | Full | 2013-07-01 | 2014-07-30 | 2014-10-31 | Technically never finished | Technically never finished | Jeff Gilligan | David Taylor
Parent Relations | Constituent Relations | Full | 2013-11-01 | 2014-05-30 | 2014-11-30 | 2014-12-30 | 1 year | Andy Perrine | Sherry King
Reporting | Information Services | Full | 2015-03-01 | 2015-08-31 | 2015-11-30 | 2016-03-26 | 1 year | Robin Bryan | Brad Kurtz
Strategic Gifts | Development | Full | 2017-07-01 | 2018-01-19 | 2018-04-19 | 2018-07-09 | 1 year | Sheila Smith | Cynthia Cline
Annual Giving | Constituent Engagement | Full | 2017-02-03 | 10/01/2017 | 01/15/2018 | 02/15/2019 | 2 years | Jeff Gilligan | Gretchen Armentrout
Communications | Communications & Marketing | Full | 2017-07-01 | 2018-02-01 | 2018-12-01 | 2019-06-11 | 2 years | Cannie Campbell | Bill Wyatt
Business Applications | Information Services | Full | 2018-07-01 | 2018-06-25 | 2019-04-01 | 2019-06-11 | 1 year | Weston Hatfield | Barry King
Prospect Research | Planning & Operations | Full | 2019-02-18 | 2109-08-18 | 2019-11-18 | 2019-12-18 | 10 months | Debbie Jordan | Martin O'Donoghue
Alumni Relations | Constituent Engagement | Full | 2019-08-21 | 2020-02-21 | 2020-08-17 | 2020-09-30 | 13 months | Sheila Smith | Carrie Combs | Committee delayed due to COVID-19 and move to telecommuting for the university in March.
Advancement Marketing | Communications & Marketing | Full | 2020-03-23 | 2020-12-04 | 2021-03-26 | 2021-04-16 | 14 months | Sheila Smith | David Taylor
Donor Relations | Planning & Operations | Full | 2017-10-01 | 2019-02-19 | 2019-05-19 | Technically never finished | Technically never finished | Andy Perrine | Linda Elliott | Experienced delays due to COVID-19
Advancement Relations* | Planning & Operations | Full | Department was desolved in May 2021
Recruitment Marketing | Communications & Marketing | Full | 2020-07-01 | 2021-03-30 | 2021-08-01 | 2021-11-10 | 16 months | Weston Hatfield | Chris Meyers | Delayed due to COVID-19

## By Department
DEPARTMENT | DATE 1st Review Completed | DATE 2nd Review Starts
Annual Giving | 2011-09-15 | 2017-02-03
Donor Relations | 2012-02-15 | 2017-10-01
Alumni Relations | 2012-01-31 | 2017-10-01
Prospect Research | 2014-01-31
Planned Giving | 2014-07-08
Gifts/Records | 2014-06-05
Marketing | 2014-11-30
Parent Relations | 2014-12-30
Reporting | 2016-03-26
Business Applications
Communications
Strategic Gifts
Corp/Found Rel.
Advancement Resources
Branded Content
Recuitment Marketing
Digital Marketing