## Table 1
Student Affairs Program Review Schedule Updated June 2021
Unit | Director/ Program Review Lead | Previous Reviews | Initial Meeting with AVP, & Dir. Dept. Will be Reminded 6 Months in Advance | Phase 1: Self- Study Begins 1 Month After Initial Meeting | Self Study Due to AVP, VP, and External Team 5-6 Months After Start | Phase 2: On-Site External Review Begins 1 Month After Self Study Due | External Review Draft Due to AVP & Director 1 Month After Review | Phase 3: Action Plan Due to AVP and VP 2 Months After External Review Report | Meet with AVP and VP within 1 Month | Brief Staff on Final Action Plan within 2 Weeks | 6 Month Action Plan Check with VP and AVP | AVP Area
Disability Services | Valerie Schoolcraft | 00, 09, 14 | Jan. 2021 | Feb. 2021 | July-August, 2021 | Aug-Sept. 2021 | Oct. 2021 | Dec. 2021 | Jan. 2022 | Jan. 2022 | July, 2022 | DEI
Residence Life | Kevin Meaney | 05, 09, 14 | May, 2021 | June, 2021 | November, 2021 | Jan. 2022 | Feb. 2022 | April, 2022 | May, 2022 | May, 2022 | Nov. 2022 | SL
SOGIE | Jennifer Iwerks | NA w/UHC | Aug. 2021 | Sept. 2021 | March, 2022 | April, 2022 | May, 2022 | July, 2022 | August, 2022 | August, 2022 | Feb. 2023 | DEI
University Health Center | Kristina Blyer | 03, 10, 15 | Jan. 2022 | Feb. 2022 | July- August, 2022 | Aug-Sept. 2022 | Oct. 2022 | Dec. 2022 | Jan. 2023 | Jan. 2023 | July, 2023 | WB
Community Service-Learning | Steve Grande | 06, 11, 16 | May, 2022 | June, 2022 | November, 2022 | Jan. 2022 | Feb. 2023 | April, 2023 | May, 2023 | May, 2023 | Nov. 2023 | CELT
OSARP | Wendy Lushbaugh | 06, 11, 17 | Aug. 2022 | Sept. 2022 | March, 2023 | April, 2023 | May, 2023 | July, 2023 | August, 2023 | August, 2023 | Feb. 2024 | SL
Dean of Students | TBD | NA | Jan.2023 | Feb. 2023 | July-August, 2023 | Aug-Sept. 2023 | Oct. 2023 | Dec. 2023 | Jan. 2024 | Jan. 2024 | July, 2024 | VPSA
Student Life | Jen Grossman-Leopard | NA w/UU | May, 2023 | June, 2023 | November, 2023 | Jan. 2023 | Feb. 2024 | April, 2024 | May, 2024 | May, 2024 | Nov. 2024 | SL
University Recreation | Eric Nickel | 01, 07, 13, 18 | Aug. 2023 | Sept. 2023 | March, 2024 | April, 2024 | May, 2024 | July, 2024 | August, 2024 | August, 2024 | Feb. 2025 | WB
University Unions | Dave Barnes | 05, 12, 17 | Jan.2024 | Feb. 2024 | July-August, 2024 | Aug-Sept. 2024 | Oct. 2024 | Dec. 2024 | Jan. 2025 | Jan. 2025 | July, 2025 | SL
University Career Center | Libby Westley | 02, 07, 12, 18 | May, 2024 | June, 2024 | November, 2024 | Jan. 2025 | Feb. 2025 | April, 2025 | May, 2025 | May, 2025 | Nov. 2025 | CELT
Orientation | Sarah Sunde | 00, 09, 14, 19 | Jan.2025 | Feb. 2025 | July-August, 2025 | Aug-Sept. 2025 | Oct. 2025 | Dec. 2025 | Jan. 2026 | Jan. 2026 | July, 2026 | CELT
CMSS | Valarie Ghant | 03, 08, 13, 20 | May, 2025 | June, 2025 | November, 2025 | Jan. 2026 | Feb. 2026 | April, 2026 | May, 2026 | May, 2026 | Nov. 2026 | DEI